## Sheet1
SafeWisdom Software Project Schedule | [7 empty] | [Gantt Chart]
| Project Start Date | 2023-03-17 |  |  |  | Display Week | 8 | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14
| Project Lead | Chai Ying | [5 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12
 | time axis 2023-05-01 to 2023-06-18
WBS | TASK |  | PREDECESSOR | START | END | DAYS | DONE % | time axis 2023-05-01 to 2023-06-18
1 | Planning
1.1 | Decided project |  |  | 2023-03-04 | 2023-03-15 | 11 | 100%
1.2 | Edit Title |  |  | 2023-04-13 | 2023-04-14 | 1 | 100%
2 | Analysis
2.1 | Research related App |  |  | 2023-03-24 | 2023-05-19 | 56 | 75%
2.2 | Analysis functions of App |  |  | 2023-03-24 | 2023-05-19 | 56 | 85%
3 | Design
3.1 | Blueprint [v1] |  |  | 2023-03-13 | 2023-03-31 | 18 | 80%
3.2 | Blueprint [v2] |  |  | 2023-04-07 | 2023-05-19 | 42 | 100%
3.3 | UI Design [v1] |  |  | 2023-03-09 | 2023-03-31 | 22 | 50%
3.4 | UI Design [v2] |  |  | 2023-04-14 | 2023-05-26 | 42 | 100%
4 | Testing
4.1 | UI Test |  |  | 2023-03-09 | 2023-05-26 | 78 | 100%
4.2 | Functional Test |  |  | 2023-03-24 | 2023-05-26 | 63 | 98%
Note on A6: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B6: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D6: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E6: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F6: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G6: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H6: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).